## Defect Tracking Log
DEFECT TRACKING LOG
Project Name | nopCommerce demo (Search functionality)
Program Manager | Kenan Kulović, Hasan Rahić, Šaban Gačić
Project Manager | Kenan Kulović, Hasan Rahić, Šaban Gačić
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
1 | 2026-01-08 | Kenan Kulović, Hasan Rahić, Šaban Gačić | Prazan search prikazuje alert; automation mora hendlati alert (UI blokira DOM akcije dok je alert otvoren). | Executing/Controlling | Testing | High | Dev team | 2026-01-08 | 2-4 h | New |  |  |  | Nedostaje validacija (trim) za whitespace input. | New | Medium | Executing/Controlling | Testing
2 | 2026-01-08 | Kenan Kulović, Hasan Rahić, Šaban Gačić | Samo razmaci (' ') ponekad se tretiraju kao validan unos i otvara /search bez jasne poruke (nedosljedno ponašanje). | Executing/Controlling | Testing | Medium | Dev team | 2026-01-08 | 4 h | New |  |  |  | Nedostaje ograničenje dužine inputa i/ili server-side validacija. | New | Low | Executing/Controlling | Testing
3 | 2026-01-08 | Kenan Kulović, Hasan Rahić, Šaban Gačić | Dugačak unos (100+ znakova) može usporiti učitavanje rezultata; nema jasnog feedback-a (loading indikator). | Executing/Controlling | Testing | Low | Dev team | 2026-01-08 | 2 h | New |  |  |  | Nedovoljno definisane validacijske poruke za neispravne znakove. | New | Low | Executing/Controlling | Testing
4 | 2026-01-08 | Kenan Kulović, Hasan Rahić, Šaban Gačić | Specijalni znakovi '@@@###' – nedostatak jasne validacijske poruke (samo no-result), korisnik ne zna da je unos nevažeći. | Executing/Controlling | Testing | Medium | Dev team | 2026-01-08 | 4 h | New |  |  |  | Nedostaje debounce/disable dugmeta tokom obrade zahtjeva. | New | Medium | Executing/Controlling | Testing
5 | 2026-01-08 | Kenan Kulović, Hasan Rahić, Šaban Gačić | Nakon pretrage bez rezultata, neki filteri/sort kontrola nisu dosljedno prikazani (UX nedosljednost). | Executing/Controlling | Testing | Low | Dev team | 2026-01-08 | 2-4 h | New |  |  |  | Nedovoljno jasno upravljanje state-om nakon reload-a stranice. | New | Low | Executing/Controlling | Testing
|  |  |  | Executing/Controlling | Testing | High | Dev team | 2026-01-08 | 4 h | New |  |  |  | Pogrešno ažuriranje total-a nakon uklanjanja popusta.
|  |  |  | Executing/Controlling | Testing | Medium | Dev team | 2026-01-08 | 4 h | New |  |  |  | Nedostaje recalculation logika nakon izmjene quantity.
|  |  |  | Executing/Controlling | Testing | Medium | Dev team | 2026-01-08 | 2-4 h | New |  |  |  | Ne čisti se error state nakon uspješnog apply-a.
Deployment
Post-Deployment
Note on E10: ====== ID#AAAAn_rmfi0 Julie Arnold (2023-01-09 19:26:29) Choose from the drop down box.
Note on F10: ====== ID#AAAAn_rmfiw John Casey (2023-01-09 19:26:29) Choose from the drop down box.
Note on G10: ====== ID#AAAAn_rmfio Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list
Note on K10: ====== ID#AAAAn_rmfis Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).